## CM Coaching Plan
Change Management Coaching plan
Current Date | Change Lead
2017-05-30 | Mary Jane
Key Area | Weekly Step | Status | Commence | Due Date | Completed Date | Owner | Comments | 2017-06-01
Prepare managers for change
Stakeholder Matrix | Complete Stakeholder Matrix | Complete | 2016-11-15 | 2016-11-30 | 2016-11-30 | Bob Smith
Stakeholder Matrix | Distributed for Review | Complete | 2016-11-15 | 2016-11-30 | 2016-11-30 | Mary Jane
Stakeholder Matrix | Walk Through Stakeholder Matrix | Overdue | 2017-01-20 | 2017-01-20 |  | Bob Smith
Stakeholder Matrix | Sign Off Stakeholder Matrix | Overdue | 2017-01-20 | 2017-01-20 |  | Mary Jane
Communications and Engagement Plan | Document Communications and Engagement Plan | Overdue | 2017-01-20 | 2017-01-20 |  | Bob Smith
Communications and Engagement Plan | Distributed for Review | Overdue | 2017-01-20 | 2017-01-20 |  | Mary Jane
Communications and Engagement Plan | Walk managers through Communications and Engagement Plan | Overdue | 2017-01-20 | 2017-01-20 |  | Bob Smith
Communications and Engagement Plan | Sign Off Communication and Engagement Plan | Overdue | 2017-01-20 | 2017-01-20 |  | Bob Smith
Communications | Develop communications materials | Overdue | 2017-01-20 | 2017-01-20 |  | Bob Smith
Communications | Distribute communication materials to managers for sign off | Overdue | 2017-01-20 | 2017-01-20 |  | May Jane
Communications | Obtain sign off for communication materials | Overdue | 2017-01-20 | 2017-01-20 |  | Mary Jane
Training
Training Needs Analysis | Complete Training Needs Analysis | Overdue | 2017-02-20 | 2017-03-20 |  | Bob Smith
Training Needs Analysis | Review Training Needs Analysis with Working Group | Overdue | 2017-02-20 | 2017-03-20 |  | May Jane
Training Needs Analysis | Sign off Training Needs Analysis | Overdue | 2017-02-20 | 2017-03-20 |  | Bob Smith
Training Materials | Training Material Development | Overdue | 2017-02-20 | 2017-03-20 |  | May Jane
Training Materials | Training Material Distribution | Overdue | 2017-02-20 | 2017-03-20 |  | Bob Smith
Training Materials | Training Material Walk Through | Overdue | 2017-02-20 | 2017-03-20 |  | May Jane
Training Materials | Training Material Sign Off | Overdue | 2017-02-20 | 2017-03-20 |  | Bob Smith
Training Logistics | Identify Training Venues | Overdue | 2017-02-20 | 2017-03-20 |  | May Jane
Training Logistics | Distribute Training Invitations | Overdue | 2017-02-20 | 2017-03-20 |  | Bob Smith
Training Delivery | Delivery of training sessions | Overdue | 2017-02-20 | 2017-03-20 |  | May Jane
Coaching support
Coaching support | Identify coaches resources | Overdue | 2017-02-20 | 2017-03-20 |  | Bob Smith
Coaching support | Explain manager as coach role | Overdue | 2017-02-20 | 2017-03-20 |  | May Jane
Coaching support | Train coaches | Overdue | 2017-02-20 | 2017-03-20 |  | Bob Smith
Coaching support | Provide coach assistance | Overdue | 2017-02-20 | 2017-03-20 |  | May Jane
Lead employees through change
Lead employees through change | Managers as coaches introduce employees to change | Overdue | 2017-02-20 | 2017-03-20 |  | Bob Smith
Lead employees through change | Managers as coaches guide through change; outside training | Overdue | 2017-02-20 | 2017-03-20 |  | May Jane
Lead employees through change | Managers as coachesguide through change post training | Overdue | 2017-02-20 | 2017-03-20 |  | May Jane
Support managers
Support managers as coaches | Provide follow up supprt | Overdue | 2017-02-20 | 2017-03-20 |  | May Jane
Support managers as coaches | Collect performance data (run buy-in index survey) | Overdue | 2017-02-20 | 2017-03-20 |  | Bob Smith
Support managers as coaches | Analyse performance data | Overdue | 2017-02-20 | 2017-03-20 |  | May Jane
Support managers as coaches | Conduct coaching debrief session 1 | Overdue | 2017-02-20 | 2017-03-20 |  | May Jane
Support managers as coaches | Conduct coaching debrief session 2 | Overdue | 2017-02-20 | 2017-03-20 |  | Bob Smith
Support managers as coaches | Conduct coaching debrief session 3… | Overdue | 2017-02-20 | 2017-03-20 |  | Bob Smith